Monitoring Animals at Risk

Version 1.0 02/04/2018

Author Names	ID Number	Email/Phone
Alexander Knapik 3543757 s3543757@student.rmit.edu.au

Manager Responsible (Tutor)	Email/Phone
Tyler Steane	tyler.steane@rmit.edu.au

Audience	:	Farmers, Veterinarians

Justification :	This document aims to propose an economical system for the early detection and or prevention of illness and injuries in farm animals at risk.

# 1 Executive Summary

Farming in Australia is a multi billion dollar business and farmers need a method to protect their assets and livelihood. To achieve this, a system tracking individual animal locations over time is proposed to prevent or detect early signs of illnesses within livestock herd. The project will consist of three different outcomes, firstly an android phone application for user interaction and displaying information in a clear and a convenient form. Secondly a GPS tracking system designed to be affixed to an animal and survive a range of conditions. Lastly, a battery charging system providing a method to charge many different batteries used in the tracker at once and efficiently.
Key deliverables include:
- Completion of the phone application by 22 May 2018.
- GPS tracker and battery charging system designed by the end of 2018.
- Bringing the product to market before 2019 end of financial year.
Resource requirements involve a small team of hardware and software engineers for design, and a marketing team to advertise the solutions. All employees are expected to be compensated satisfyingly, and an equipped office is necessitated for both teams which includes various test equipment necessitated for the engineers.
Before retailing the product, a testing period will be required to evaluate and troubleshoot the solutions proposed to ensure reliability. Communication with agriculturists and customers is essential in developing an appropriate solution to be accepted by a varied amount of users, from suiting small to large farms.
The product is intended to be marketed as an investment, proposing a system for increasing livestock produce to be recouped from the benefits offered.

# 2 Table of Contents

# 3 Configuration Management
## 3.1 Revision Information

Version Number	Changes from earlier revision.
1.0	Initial Version.

## 3.2 Acronyms & Abbreviations

1. RA	Requirements Analysis.
2. DP	Design Proposal.
3. RCM	Regulatory Compliance Mark.
4. EMI	Electromagnetic Interference.
5. GPS	Global Positioning System.
6. IDE	Integrated Desktop Environment.
7. API	Application Programming Interface

# 4 Introduction, Overview & Scope

Beef and veal accounted for $13.1 billion dollars of production from 2015 to 2016 in Australia, with milk alone tallying $4.2 billion.[1] Figure 1 depicts the value of these recorded livestock commodities. Animals, like all living beings develop illnesses. Specifically within livestock, poor welfare is associated with decreased produce, whether it be milk by cows, fleece from sheep, or just general growth and reproduction rates.[2] This greatly impacts farmers who’s income directly relate to the well being of their livestock.

Figure 1 – Value of Livestock Commodities Produced in Australia in millions of dollars [1]
Value of Livestock Commodities Produced in Australia 2015 - 2016
Value ($million)

However, there are key identifiable signs when an animal’s welfare has declined. For example, within cattle, depression observable from lethargy, and declined appetite or inability to walk are tell tale signs of either illness, or physical injuries.[3] Furthermore, depression and severe lameness are also perceptible signs of problems within sheep[4].

Livestock also have certain requirements and needs, the basics consisting of food, water and shelter. However, livestock are susceptible to weather extremities. Especially within Australia, heat stress is an issue and in extremely hot days, animals necessitate an increased access to water, and shade from the sun.

Although a vigilant eye is valuable, it can be difficult to monitor and track the location of each animal manually. Farmers are increasingly requiring an automated process which can track their animals throughout the day, in numerous weather conditions. Notification of issues with their livestock including accompanying information is essential to communicate with veterinarians. Farmers require a system that can:

- Track the location of an animal with respect to time for detecting lethargy or lameness.
- Detect whether an animal has not been to either a feeding or drinking trough, and shade.
- Be easily used for observing animal behaviour on a map.

# 5 Key Requirements & Understandings

## 5.1 Guiding Principles
- The product shall be in the form of an Android application.
- The Android software shall be able to interpret GPS coordinates as positions on a map which should come from a transmitter attached to an animal.
- The user shall be allowed to enter defined areas to generate an alarm whether an animal has or has not been located within the area.
- There shall be a system to search for information regarding a single animal.
## 5.2 Requirements
- Users of the product must be able to plan and establish a logistical system which takes into account for battery drain and recharging multiple devices.
- The GPS tracking device is to be weather and impact resistant due to the harsh conditions that may be present.
- The GPS tracker must adhere to Australian standards and be tested for RCM compliance before being put on the market.
- Many different phones must be updatable simultaneously with the same GPS location data accounting for different workers on a single farm.
- Each tracker must transmit secure data to prevent undesirable spying.
- Arrangements with farmers to be made for small scale testing of the device before marketing.
- The tracker must not emit a non compliant amount of EMI.
- The product will have a long life span and be reusable for different animals.
## 5.3 Constraints
- Cellular communications requires larger batteries with reduced time between charging in comparison to low power alternatives.
- A standard power point can not supply more than 2.4kW which will be used for charging many batteries simultaneously.
- Limited to one software engineer developing the phone application.

## 5.4 Assumptions
- Potential stakeholders use an Android operating system on their phone.
- Farmers will be willing to see the product as a return of investment.
- Android will continue being supported well into the future.
- The cellular communications interface will continue being supported well into the future.
- The whole range of marketable products is tax deductible by farmers.

# 6 Solution Description

The Android Studio IDE shall be used to develop the phone application. The programming will be done with the Java language, and the GUI will be designed with XML.

The initial GUI may consist of 3 main elements:
- Google Maps API used as a map to observe most recently transmitted GPS coordinates of each individual animal.
- A search function which can identify a single animal and present user definable information such as animal type, age, pregnancy status and past medical history. From this menu, a map will be available depicting the path a distinct animal has taken over a day by utilising polylines available within the API.
- A zone creator utilising polygons within the API to be drawn on a map with user defined functions to raise alarms in the case of issues.

The GPS tracking transmitter will be attached to the animal via an adjustable collar. It should transmit GPS location, time, battery percentage and a unique identifier in the form of a network packet to the user’s phone via mobile telecommunications such as 3G or 4G. It will be designed to stay attached on an animal at all times regardless of the conditions and should be able to send information about a low battery that needs charging, which the phone will then process into an alert.

Local databases will be used to store the following:
- All of the information regarding animal location consisting of the GPS coordinates with corresponding time and identifier.
- User defined animal information.
- User defined map information consisting of GPS coordinates forming a polygon including matching functions.

The following figure displays the basic elements and progression of menus within the Android application GUI.

MAIN
MENU

MAP
VIEW
ANIMAL
SEARCH &
LIST
LIST OF
DEFINED
AREAS

AREA
CREATOR
WITH MAP
DEFINE
AREA
FUNCTIONS

SPECIFIC
ANIMAL
INFORMATION

SPECIFIC
ANIMAL
TRACKING

Figure 2 – Monitoring Animals at Risk GUI Design

# 7 Solution Path

The project will undergo a prototyping life cycle where a cyclical approach of designing and building prototypes are undertaken to present to clients, ensuring that the direction of the project is accordance with the initial requirements. The prototyping stages are outlined in the following table.

#	Prototype Purpose	Details
1	Develop basic UI	Create basic main menu which can move to different XML activities.
2	Integrate Google Maps API	Have a basic Map UI in with random markers to simulate displaying animal locations.
3	Prove GPS integration	Use a laptop to send a network packet via Wi-Fi to the phone containing essential data used for representation on a map.
4	Prove that GPS data can connect with Google Maps API	Process the data packet sent from a laptop into a marker onto the map with relevant information.
5	User definable areas	Have polygon areas definable by GPS coordinates relative to a map.
6	Integrate databasing	Develop a system to allow for storing information regarding the user areas and animal information.
7	Add specific functions to user areas	Organise a system which checks the stored database information and sends an alert to the phone whether an animal has or hasn’t been to a certain area by a specific time.
8	Finalise GUI	Clean up GUI design to ensure it fits a wide range of phones. Converse with the client to ensure the design it to their liking.
9	Weather report functionality	Integrate a weather API which can take forecast data and include it as part of the functions related to user areas.
10	Create GPS tracker	Develop a tracker which can be attached to an animal which periodically sends GPS location data to the phone via cellular data.
11	Design charging system	Present a system which can charge many batteries at once.

For the assessment deadline of 22 May 2018, the project is expected to complete up to step 8, with most of the software expecting to be finalised. A stretch goal within this time period will include phone GPS data to provide for localised temperature forecasts supporting user defined areas for corresponding alerts.

Due to time constraints, a laptop will be used as a replacement for the GPS tracker to send network packets in simulation. Furthermore, as animals will not be available for testing, artificial data will be used for testing the various behaviours of the software.

Steps 1 to 9, 10 and 11 will be designed simultaneously.

# 8 Risks, Opportunities, and the Test Plan

## 8.1 Risk Analysis and Elimination
Risk	Risk Analysis & Risk Elimination Activities
Battery life renders the product inefficient	Major. / Consult with farmers to develop effective logistics plans based on battery life estimates early in the project. Consider other low power alternatives to cellular telecommunications.
High power charging solutions required for large farms may cause an electrical and fire risk in the event of an accident.	Moderate. / Ensure that the products are designed well with this in mind, and inquire independent third party testing specialising in safety.
Project exceeds contract deadline	Major. / Plan all dates and events in advance. If there is still an issue, make considerations into hiring more employees.

## 8.2 Testing Considerations
Simulated data will initially be used for the initial testing of the phone application in both qualitative and quantitative methods. Once the tracker is developed, stakeholders will be responsible for evaluating the proposed solution, communicating any needed adjustments and as a resource for qualitative data gathering in a real world scenario. Two weeks will be required for final testing of data gathering, for which one week will be needed afterwards for troubleshooting.

# 9 Project Management

## 9.1 Resource and Skill Acquisition
Staff must become acquainted with farmer and livestock requirements, the various types of injuries and diseases that livestock may face and the observable signs associated for automated detection. Access to a farm will be required for product testing and evaluation will be required. This will be organised via writing.
## 9.2 Configuration Management Plans
Once development of the phone application is complete, the software engineering team is to shift their focus into designing the embedded software for the GPS tracker.
## 9.3 Cost Estimates
A rough estimate of development costs entail:
- $600,000 AUD for employee salary.
- $50,000 AUD for manufacture tooling.
- $50,000 AUD to test compliance of the products in each market.
The tracking system is intended to sell for under $200 AUD, with charging solutions ranging depending whether customers requires a consumer or industrial grade solution.

## 9.4 Time Plan

Activity	3 / Apr	10 Apr	17 Apr	24 Apr	1 May	8 May	15 May	22 May
Develop basic UI
Integrate Google Maps API
Receive network packets with phone
Connect network data with map API
Initialise user definable areas.
Add functions to user areas
Clean up GUI
Testing
Include Weather report functionality

Key dates include:
- Phone application completion: 22 May, 2018.
- Products designed and tested: 01 Dec, 2018.
- Contract due: 31 May, 2019.

# 10 References

[1] Australian Bureau of Statistics. “Value of Agricultural Commodities Produced, Australia, year ended 30 June 2016.” Internet: http://www.abs.gov.au/ausstats/abs@.nsf/mf/7503.0, Jul. 27, 2017. [Apr. 01, 2018].
[2] Meat & Livestock Australia. “Diseases.” Internet: https://www.mla.com.au/research-and-development/animal-health-welfare-and-biosecurity/diseases/, 2016. [Apr. 01, 2018].
[3] The Beef Site. “Identifying Sick or Injured Cattle.” Internet: http://www.thebeefsite.com/articles/2038/identifying-sick-or-injured-cattle/, Jul. 2009. [Apr. 01, 2018].
[4] E. Litzow. “Sheep Diseases the Farmers’ Guide.” Biosecurity SA. [Apr. 01, 2018].

# 11 Marking & Tutor Comments
This document should have given you a very good feel for what the student aims to achieve. Before starting to read and mark, turn on tracking (Edit->Changes->Record) and make any comments or changes to the student text as you read.
Note also the General Marking Guide at the end of the Project & Laboratory Guide document.

Page Lengths: each section should be at maximum-
- Title page, one page long.
- 1: Executive summary, one page long.
- 3: Configuration Management, one page.
- 4: Introduction, two pages.
- 5: Key Requirements, two pages.
- 6: Solution Description, 3 pages.
- 7: Solution Path, one page.
- 8: Risks, one page.
- 9: Project Management, one page.
Expect quite brief statements in subsections not identified in the marking guide below.

Marking Guide: note the general marking guide at the end of the main lab guide.

Item	Percent Allocated	Percent Achieved
Overall readability, good grammar and good spelling. Document kept short with no padding.	20%	18
Executive Summary and Introduction are clear and give a good vision of the project. (1 and 4) Filled in details on front page.	15%	12
Key requirements are clearly stated and make sense. (5)	15%	14
Solution Description clearly identifies the software and hardware that will successfully implement a solution. (6)	30%	28
Solution Path outlines at least 4 prototype deliveries that in theory could be shown to you and get some marks. (7)	15%	15
Risks and Project Management: risks are clearly stated, time plan covers at least semester deadlines and some intermediate deliveries (8 and 9). do not expect a lot of work in this section apart from that on risks.	5%	5
Total (sum automatically calculated)	100%	92

Comments: Add a comment, at least an overall impression, in the box below-

Overall Comments / Really well written. And covered the project well. / I think it would be helpful for you to have another go at the introduction and make sure you cover your solution and how it benefits all the different stakeholders. / Great work.